WORK ORDER

Customer: Better Companies LLC.

Effective from: [To be confirmed], Subject to the receipt of the signed Work Order (this document)

This Work Order (“WO”) forms part of the Master Services Agreement (the “Agreement”) dated October 06, 2025, entered into by and between Better Companies LLC., with registered office at 2525 Main St Ste 500, Irvine, CA 92614 (“Customer”), and Artizent Inc. (formerly Nous Infosystems Inc.), with registered office at 200 Metroplex Drive, Suite 302, Edison, NJ 08817 (“Artizent”/“Service Provider”).

Engagement Model: Fixed Price.

##### Executive Summary

Better Companies is a consumer financial services company operating multiple brands across debt relief, tax relief, consumer lending, and business capital. Its high-volume call center supports daily customer interactions, negotiations, advisory services, and account resolution across these offerings.

### Current Situation and Business Needs

- Project ELEVATE has established the Microsoft Fabric foundation

- A governed Gold layer is already available for analytics

- More than 60 reports support current business reporting

- Insights remain distributed across a broad report estate

- Users must know which dashboard contains the answer

- Business users need plain-English and spoken questions

- Trend and variance answers should be computed live

- Leaders need predictive insight from Gold-layer history

- Slack is the primary channel for sharing and action

### Strategic Business Objectives

- Faster Decisions

  - Give leaders direct answers in plain English

  - Reduce dependence on dashboard navigation

- Broader Adoption

  - Bring insight into Slack, chat, and voice

  - Expand access beyond report specialists

- Trusted Insight

  - Ground every answer in governed Gold data

  - Reconcile results to the Power BI baseline

- Forward View

  - Combine trend, variance, and prediction

  - Label forecasts and confidence clearly

- Control by Design

  - Preserve three-tier role-based access

  - Protect PII and retain a complete audit trail

- Cost Transparency

  - Route each request to the best-fit model

  - Show usage and spend transparently

### Expected Outcomes

- Role-appropriate answers for Agent, Manager, and Executive users

- PII protection, guardrails, and a complete audit trail

- Answers validated against the Power BI question-bank baseline

- Transparent model routing, usage, and cost control

### Key Challenges

- Business, Data & Analytics

  - More than 60 reports make insight discovery difficult

  - Users depend on dashboard knowledge to locate answers

  - Data dictionary and dataset groupings require hardening

  - Priority Power BI measures must be reverse-engineered

  - The 20–50 question bank must represent real business questions

  - Historical data must support two useful predictive models

  - Forecasts must be labeled and supported by confidence measures

  - Answers must reconcile with the Power BI baseline

  - New questions must not require new report development

- Technology, Governance & Delivery

  - Slack application approval and tenant access must be ready

  - Azure OpenAI and Azure AI Speech must be enabled

  - Three-tier RBAC, PII masking, and audit controls must hold

  - SME availability and timely phase approvals are critical

  - Voice, load, security, adoption, and cost must be validated before go-live

### Customer has engaged Service Provider to provide the following services:

- Build a production conversational AI assistant over the governed Gold layer

- Deliver live trend, variance, and persona-based analytics

- Train and operationalize two predictive models with labeled forecasts

- Provide Agent, Manager, and Executive experiences aligned to role

- Preserve RBAC, mask PII, apply guardrails, and retain audit logs

- Deliver Slack, GPT-style chat, voice, and an administration console

- Implement model routing, usage metering, and cost controls

- Validate answers against the Power BI question-bank baseline

- Deploy the solution, deliver runbooks and knowledge transfer, and provide two weeks of hypercare

##### Project Summary

Better Companies has established a strong analytics foundation through Project ELEVATE, including Microsoft Fabric, a governed Gold layer, and more than 60 business reports. Accessing insights, however, still depends on users knowing which report or dashboard contains the required information, limiting decision-making speed and accessibility.

The engagement will enable business users to obtain trusted answers through plain-English or spoken questions. It supports Better Companies’ objectives of broadening access to insight, reducing reliance on report specialists, accelerating decisions, and extending analysis from historical reporting to forward-looking insight.

Artizent will deliver a production-grade conversational AI capability over the governed Gold layer. The solution will provide natural-language querying, live trend and variance analysis, persona-based insight, and two predictive models through Slack, a GPT-style chat interface, voice capabilities, and an administration console. Role-based access, PII protection, responsible-AI guardrails, auditability, model-routing controls, and cost visibility will remain integral to the solution.

##### Project Scope

### Discovery and requirements

- Conduct discovery workshops to validate the agreed scope, priority use cases, user personas, and success criteria.

- Review and refine the existing Gold-layer data dictionary.

- Organize relevant facts and dimensions into governed dataset groupings.

- Reverse-engineer priority Power BI reports and semantic measures used as the business baseline.

- Review and tag the agreed 20–50 business-question bank for development and validation.

### Solution and data design

- Produce the solution architecture blueprint and confirm implementation acceptance criteria.

- Define the Agent, Manager, and Executive access model.

- Document the applicable RBAC rules and PII field mappings.

- Define query-planning, semantic-binding, and answer-composition rules.

- Assess AI workload headroom against the customer’s existing Microsoft Fabric capacity.

### Development, analytics, and integration

- Develop conversational natural-language querying over the governed Gold layer.

- Implement live month-over-month, quarter-over-quarter, and year-over-year analysis.

- Generate charts and trend visualizations when appropriate to the user’s question.

- Develop persona-based analytics for Agent, Manager, and Executive users.

- Train and operationalize two predictive models using approved Gold-layer history.

### Channels, security, and quality controls

- Manage predictive models and experiments through MLflow and score approved outputs back to Gold.

- Configure model routing based on query type, token thresholds, cost, and approved manual overrides.

- Deliver Slack as the primary interaction channel with customer-approved SSO and application access.

- Configure the GPT-style chat client, voice input/output, and administration console.

- Implement RBAC enforcement, PII masking, responsible-AI guardrails, audit logging, cost metering, and automated evaluation controls.

### Testing, deployment, and support

- Validate responses against the Power BI baseline and agreed question bank.

- Perform what-if, PII red-team, voice accuracy, latency, load, cost, and regression testing.

- Facilitate three-tier UAT and address approved findings before production release.

- Deploy the approved Slack application and administration console to the production environment.

- Deliver operational runbooks, knowledge transfer, formal handover, and two weeks of hypercare.

##### Project Management

- Project Governance & Accountability – Establish project governance, roles, responsibilities, decision rights, escalation mechanisms, and primary engagement leadership across the parties.

- Planning & Delivery Management – Manage project scope, workstreams, resources, dependencies, schedules, milestones, delivery gates, and overall execution in accordance with the agreed project plan.

- Requirements & Change Management – Facilitate requirements validation, establish and maintain the approved baseline, manage acceptance criteria, and assess and govern changes through the agreed change-control process.

- Stakeholder & Customer Management – Coordinate with customer sponsors, SMEs, engineers, and stakeholders to drive timely decisions, approvals, issue resolution, reviews, testing, and acceptance.

- Risk, Issue & Dependency Management – Proactively identify, track, mitigate, and escalate risks, issues, assumptions, dependencies, and decisions, with clear ownership and resolution timelines.

- Progress, Reporting & Executive Oversight – Conduct appropriate project governance forums, sprint reviews, status reporting, and steering reviews covering progress, schedule, financials, risks, dependencies, decisions, and key actions.

- Quality, UAT & Go-Live Management – Coordinate quality assurance, phase-gate reviews, customer acceptance, UAT, deployment planning, go-live readiness, and required customer/third-party approvals.

- Transition & Hypercare Management – Govern production transition, knowledge transfer, documentation, formal handover, hypercare, and transition to ongoing support in accordance with the agreed acceptance and support model.

##### Project Deliverables

| Discovery | Build | QA | UAT & Hardening | Production |
| --- | --- | --- | --- | --- |
| - Hardened Gold data dictionary - Dataset grouping (facts & dims) - Baseline pack: top-20 reports + semantic measures, reverse-engineered - Tagged 20–50 question bank - RBAC & PII field map, compliance-signed - Architecture blueprint + SOW acceptance criteria | - Working agent in Dev: NLQ + trend / variance - 2 predictive models scored to Gold - Slack app · chat client · voice · admin console - Model router live, cost meter running - Guardrails + automated eval harness - A recorded demo every two weeks | - Baseline validation report: question bank vs Power BI, answer by answer - What-if & PII red-team results - Voice test report (accuracy, latency) - Load & cost test vs 500 queries/day - Regression suite — handed to your team | - UAT sign-off from all three tiers - Guardrail ruleset tuned on real user phrasing - Admin, routing & incident runbooks - Knowledge transfer sessions delivered - Go-live readiness checklist, jointly signed | - Slack + admin console live in production - Hypercare: 2 weeks, same-day response - Hypercare log & closure report - Formal handover - your team runs it |

##### Exclusions from Scope

- External & Financial Data Sources – Data sources outside the governed Gold layer, including macroeconomic, NetSuite, ERP, and other financial data not available in the Gold layer.

- Unstructured Data – Ingestion, processing, or integration of documents, files, and other unstructured data sources.

- Data Remediation & Reconciliation – Large-scale data cleansing, remediation, MDM, reference-data correction, source reconciliation, or creation/backfill of missing historical data beyond agreed semantic fixes.

- Power BI Development & Modernization – Development of net-new Power BI reports/dashboards or rebuilding, refactoring, or modernization of existing reports beyond the agreed scope.

- Source Onboarding & Data Migration – New source-system onboarding, historical backfills, data migrations, source-system corrections/reconfiguration, or new integrations not explicitly identified in the proposal.

- Data Model & Fabric Platform Changes – Physical redesign of Bronze/Silver/Gold data models or changes to core Microsoft Fabric services, capacity, or upstream/Gold-layer pipelines beyond the semantic layer.

- AI, Licensing & Infrastructure Costs – AI model retraining/monitoring/production operations beyond hypercare, Fabric capacity/SKU upgrades, infrastructure procurement, third-party tools/connectors, AI subscriptions/tokens, Azure OpenAI/Azure AI Speech, Anthropic/Claude licenses, or additional user seats.

- Post-Handover Operations & Compliance – Production administration after handover, independent regulatory certifications, legal opinions, external audits, and other ongoing operational/compliance activities not explicitly included in the SOW.

##### Project Assumptions

- Estimation & Timeline: Estimate is based on current scope and assumptions; delivery planned for 16 weeks + 2 weeks hypercare.

- Delivery & Governance: Delivery across 7 workstreams and 5 phase gates following the agreed governance cadence.

- Discovery & Scope: Discovery will validate requirements, use cases, data, architecture, dependencies, and acceptance criteria; material changes follow the Change Request process.

- Scope Caps: Agreed caps for Gold tables, datasets, semantic models, reports, and measures will be finalized during Discovery.

- Data Readiness: Gold-layer data is assumed available, complete, reliable, and fit for agreed analytics/predictive use cases; major remediation or alternate sourcing is excluded.

- Platform & Reporting Stability: Fabric, pipelines, upstream systems, semantic definitions, and Power BI baselines are assumed stable; existing reports will be reused/reverse-engineered.

- Technology & Third Parties: Required environments, access, infrastructure, and APIs will be available as needed; capacity increases, third-party licenses, AI subscriptions, and usage charges are customer-funded.

- Resources & Approvals: Artizent and customer resources will be available as planned, with timely SME inputs, security approvals, decisions, and sign-offs; delays/changes may impact scope, schedule, fees, or outcomes.

##### Project Dependencies

- Week-0 Readiness: Required environments, access, data, approvals, stakeholders, owners, and target dates will be confirmed before delivery commencement.

- Executive Sponsorship: An authorized Better Companies executive sponsor will be available for priorities, escalations, approvals, and key business decisions.

- Stakeholder & SME Availability: Required business, technical, security, and governance stakeholders will be identified and allocated; business SMEs/engineers will provide approximately 6–8 hours/week.

- Requirements & Sign-offs: Scope, requirements, business rules, use cases, priorities, and deliverables will be clarified, reviewed, and approved promptly, including timely sign-offs at the five delivery gates.

- Data & Baseline Access: Timely access to approved data dictionaries, Gold-layer mappings, business definitions, historical data, Power BI reports, semantic measures, documentation, and the 20–50 question bank will be provided.

- Technology & Environment Readiness: Required Microsoft Fabric, OneLake, Power BI, Purview, Entra ID, Slack, source systems, integrations, Dev/QA/Production workspaces, APIs, repositories, service accounts, and credentials will remain available and stable.

- Security, Testing & UAT: Customer will enable required Azure OpenAI, Speech, Slack and capacity services and complete RBAC, privacy/security reviews, defect resolution, performance/cost testing, regression testing, and three-tier UAT within agreed timelines.

- Go-Live & Change Control: Production authorization, deployment plans, runbooks, knowledge transfer, and operational readiness will be completed on time; dependency delays or changes impacting scope, effort, milestones, fees, or acceptance will be managed through formal change control.

##### Customer Responsibilities

Customer will perform the following responsibilities to support successful and timely delivery:

- Executive Sponsorship & Governance: Nominate an authorized executive sponsor and designated governance team, decision-makers, SMEs, project contacts, and technical/data/security representatives with agreed availability.

- SME Participation: Ensure qualified SMEs participate in workshops, requirements clarification, reviews, demonstrations, testing, issue resolution, UAT, and acceptance activities, typically 6–8 hours per week.

- Week-0 Readiness: Complete readiness activities and confirm owners and target dates for required environments, access, data, approvals, dependencies, and customer actions.

- Requirements & Business Inputs: Provide timely business requirements, use cases, calculation rules, terminology, scenarios, reporting expectations, priority question bank (20–50 questions), and measurable acceptance criteria.

- Data & Reporting Inputs: Provide and validate data dictionaries, dataset groupings, Gold-layer mappings, semantic models, Power BI reports/measures, baselines, and supporting documentation.

- Architecture, Security & Compliance: Provide applicable enterprise architecture, security, privacy, Responsible AI, regulatory, compliance, RBAC, PII, network, and other technical standards and requirements.

- Technology, Access & Licensing: Provision timely access to required platforms, environments, repositories, APIs, service accounts, infrastructure, workspaces, capacity, licenses, AI/cloud consumption, and third-party stakeholders.

- Validation, UAT & Acceptance: Participate in governance, reviews, defect resolution, deployment planning, three-tier UAT, and go-live activities; validate deliverables and approve milestones, runbooks, knowledge transfer, go-live readiness, and final acceptance within agreed timelines. Customer-caused delays or dependencies may impact schedule, effort, resources, fees, and outcomes and may require formal change control.

##### RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity | BC Exec Sponsor | BC Business SME | BC Data/Security SME | Artizent PM/Delivery Lead | Artizent Tech/AI Lead | Artizent QA Lead |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements & Question Bank | I | R | C | A | C | C |
| Solution Architecture & Design | I | C | C | A | R | I |
| Data Dictionary & Semantic Hardening | I | C | R | A | R | C |
| Development / Build | I | I | C | A | R | C |
| Testing & QA (Baseline Validation) | I | C | C | A | C | R |
| UAT Execution | I | R | C | A | C | R |
| Guardrail & Compliance Sign-off | A | C | R | C | R | C |
| Deployment / Go-Live | A | I | C | R | R | C |
| Change Management & Governance | A | C | I | R | C | I |

##### Team Composition

  - Delivery Leader / Scrum Master (Engagement Lead)

  - Solution Architect

  - Fabric / Data Architect

  - AI Engineer #1

  - AI Engineer #2

  - Data Engineer (ML)

  - Power BI Developer

  - Senior Quality Engineer

##### Change Management Process

- The Customer and Artizent may amend this Work Order only through a mutually executed written Change Authorization. Each Change Authorization supplements this Work Order and, in the event of conflict, will take precedence over this Work Order and any earlier Change Authorizations to the extent stated.

- When both parties agree to a proposed change, they will document its scope, impact, schedule, and commercial terms in a written Change Authorization for mutual review and execution.

- At the Customer’s request, Artizent may assess the impact of a proposed change. If the assessment requires additional effort, Artizent may charge for that analysis only after providing a written estimate and receiving the Customer’s written approval.

- A Change Request (CR) may be initiated when:

- Planned or assigned work is not identified in the Project Scope.

- Actual effort or duration exceeds the estimate because of unforeseen delays attributable to the Customer.

- The Customer requests functionality or features beyond the defined solution.

- UAT extends beyond the planned timeline because the acceptance criteria were not agreed during requirements sign-off.

- The Customer has not defined or approved UAT exit criteria.

- Functional changes are requested after UAT sign-off and production deployment.

Artizent will initiate change management when a qualifying change is identified. Following approval by the Customer PM/Sponsor, the Customer will submit a Request for Change. Work will begin only after both parties approve the applicable scope, schedule, resource, and commercial impacts in writing.

##### Milestone Schedule

| Milestones | Description | Due | Price (USD) |
| --- | --- | --- | --- |
| M1 | Conduct discovery, assess the Gold layer, validate the semantic model, refine the data dictionary, reverse-engineer existing Power BI reports, and finalize the solution architecture and implementation roadmap. | Week 4 | $37,000 |
| M2 | Build the core conversational AI assistant and implement governance, security, RBAC, responsible-AI guardrails, and multi-channel interfaces. | Week 8 | $55,000 |
| M3 | Develop trend analysis, predictive insight, and persona-based analytics; implement model management, intelligent routing, and cost optimization. | Week 12 | $55,000 |
| M4 | Validate the solution against the approved question bank, complete UAT and business-user training, deploy to production, and provide hypercare support. | Week 16 | $37,000 |
| TOTAL |  |  | $184,000 |

##### Payment Terms and Other Conditions

- Invoices will be issued in accordance with the payment milestones.

- Better Companies will pay each invoice within thirty (30) days of receipt. All rates exclude applicable taxes.

- An invoice will be deemed accepted unless Better Companies reports a discrepancy to Artizent in writing within fifteen (15) business days of receipt.

- Artizent may pause further activities if an invoice remains unpaid until all overdue amounts are received and settled in full.

- Services and deliverables will be deemed accepted unless Better Companies reports a discrepancy to Artizent in writing within five (5) business days of delivery.

- Better Companies will procure the licenses required for specialized hardware, software, and third-party tools identified by the Artizent project team.

- Resources are eligible for twelve (12) leave days per year, prorated to the Work Order term; these days will be treated as working days for invoicing purposes.

- Overtime, weekend, holiday, and late-night work will be billed at 1.5 times the applicable standard hourly rate. Late-night hours are Monday through Friday, 11:00 PM to 7:00 AM IST. The same premium applies to approved work performed on weekends or holidays.

- Better Companies will provide Artizent with at least thirty (30) days’ prior written notice of non-renewal or termination of this Work Order.

##### Acceptance Criteria

Unless the parties agree to separate defect-based criteria in writing, the following measurable criteria apply at each phase gate. Sprint, milestone, and final deliverables are subject to a consistent deemed-acceptance period of five (5) business days from delivery.

| Gate | Measurable Acceptance Criteria |
| --- | --- |
| Design Approval (Gate 1) | The Better Companies Business Lead and Compliance SME approve the solution architecture, RBAC/PII field map, Work Order acceptance criteria, hardened data dictionary, and 20–50-question bank. |
| Build Completion (Gate 2) | The working agent answers NLQ and trend/variance questions in the Development environment; RBAC operates across all three tiers; Slack, the chat client, and the administration console are functional; no Critical or High defects remain open. |
| Testing Completion (Gate 3) | The question-bank answer-match rate meets the threshold agreed at Discovery; PII red-team and 500-queries-per-day load tests pass; no Critical defects remain open, and each High defect has an agreed remediation plan. |
| UAT Sign-off (Gate 4) | Designated Agent, Manager, and Executive representatives provide written sign-off; no Critical defects remain open; High defects are resolved or formally waived in writing. |
| Go-Live Approval (Gate 5) | The parties jointly sign the production deployment checklist; Better Companies accepts the hypercare plan and runbooks and confirms readiness for handover. |

##### Risks and Mitigations

| ID | Risk | Impact | Probability | Owner | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R1 | Gold layer / data dictionary less mature than represented | High | Medium | Joint | Complete a Week-1 readiness assessment against an agreed rubric. Present any rebuild requirement at the Discovery gate as a scope and cost change before Build begins. |
| R2 | Question bank arrives late or incomplete | Medium | Medium | Better Companies | Artizent will seed a starter question bank from report-usage logs to reduce impact on the QA baseline. |
| R3 | Semantic model gaps surfaced during reverse engineering | Medium | Medium | Artizent | Resolve in-scope gaps within the estimate and raise Gold-pipeline changes at the phase gate through a Change Request. |
| R4 | Business / Compliance SME availability falls short of the Resource Availability Expectations | High | Medium | Better Companies | Schedule sessions two weeks in advance. Track shortfalls week-for-week and update milestone dates through Change Management. |
| R5 | Slack app approval, or Azure OpenAI / Azure AI Speech tenant enablement, is delayed | Medium | Medium | Better Companies | Issue the Week-1 enablement checklist and sequence chat-client development to avoid dependency on Slack approval. |
| R6 | Low end-user adoption after go-live | Medium | Low | Joint | Use Slack-first delivery, engage tier champions during UAT, and track adoption on the steering dashboard from Week 12. |

For, Better Companies LLC

Name:						Signature	: ______________________

Title:						Date		:

For Artizent Inc.

Name:						Signature	: ______________________

Title:						Date		: